## Gantt
Project timeline template (Gantt)
Project start: |  |  | 2027-09-13 |  | Example: product launch campaign (overwrite or delete)
Enter start and end per row; the bars colour themselves. Grid: working days only (Mon–Fri). Online with your team and planned vs actual: planomatti.com/en/project-timeline/
Task | Type | Owner | Start | End | Working days
Briefing and goals | Task | Maya | 2027-09-13 | 2027-09-14
Audience and key message | Task | Maya | 2027-09-15 | 2027-09-17
brief approved | Milestone | Maya | 2027-09-17 | 2027-09-17
Copy and content plan | Task | Leo | 2027-09-20 | 2027-09-27
Visuals and video | Task | Ana | 2027-09-20 | 2027-09-29
Landing page | Task | Sam | 2027-09-28 | 2027-10-01
Ads and tracking setup | Task | Sam | 2027-10-04 | 2027-10-06
Final review and fixes | Task | Maya | 2027-10-07 | 2027-10-08
Buffer | Task | – | 2027-10-11 | 2027-10-12
campaign live | Milestone | Maya | 2027-10-12 | 2027-10-12
Run and optimise ads | Task | Sam | 2027-10-13 | 2027-10-22
results report | Milestone | Maya | 2027-10-22 | 2027-10-22